**MONITORING SHEET FOR OPERATIONAL PLAN 2014**

1ST and 2nd Quarter

**OFFICE:** Research and Extension

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **MFO** | **SPG** | **PROJECT/ACTIVITY** | **PERFORMANCE INDICATOR** | **BASELINE****2013** | **ACTUAL OUTPUT**(January-June) | **ACTUAL BUDGET SPENT**(Jan-June) | **ASSESSMENT****(DIFFICULTIES/REMARKS)** | **RECOMMENDATIONS** |
| MFO3 | SPG3 | R&D Implementation | No. of studies completed | 58 | 25 | P100,000 | - Unpredictable weather conditions disturbed implementation |  |
| No. of on-going studies | 50 | 40 | 5M | Procurement procedures delayed implementation of research activities | - Dialogue with Admin on how to fast track procurement  |
| No. of approved proposals | 30 | 20 | P200,000 | 5 proposals did not fall under research priority areas  | -Update research priority areas |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |